## Sheet1
WeeK 1 | Project-21 Devanshi Trivedi
Start date- 10/27/2016
End Date- 11/2/2016
Task | Description | Hours
Meeting with the sponsor OCT-27 | Introduction of the project and agreement upon the work timing for the project and resolving the ongoing project selection issue. | 45 Min
Introduction of the project | Introduction of the project and prototype and how much work is already done | 15 Min
Introduction to the project mates | Introduction to the project team mates. | 15 Min
Understanding the architecture of the project | Understanding the project architecture | 30 Min
Preparing the Intial charter | preparing the intial project charter Using the IEEE format | 6 Hours
Preparing the intial Project Management Plan | Preparing the intial project managemet plan using IEEE format | 6 Hours
Preparing the meeting minutes | Preparing the meeting minutes of OCT-27 and NOV-2 | 1 Hour
meeting with the sponsor-NOV 2 | Change in working the project for which the chartr was alredy created | 5 Min
Regular class meeting | Discuss the change in projct related issues. | 30 Min
| Total | 15 Hr 20 Min
Week2
Start Date - 11/3/2016
End Date - 11/9/2016
Task | Description | Hours
Going through the code of PR Portal Project | Understanding the architecture of the new already done project which I ma going to extend | 6 Hours
Meeting with the entire team and sponsor | The main developer of the PR Portal project gave the idea of the Project | 1 Hour 30 Min
Preparing The Charter Again | For new Project | 6 Hours
Preparing the Project management plan again | For new Project | 6 Hours
Preparing the meeting minutes | Desciption and understanding of the discussion in the meeting | 30 Min
Regular class Meeting | Discuss the ongoing problems | 30 Min
| Total | 20 Hour 30 Min
Week3
Start Date - 11/10/2016
End Date - 11/16/2016
Task | Description | Hours
Understanding the reuirement and design | Understanding the modules nad identifying the modules which nedds to be changed | 4 Hours
Preparing the design Documents | Detailed design documentation using IEEE Format | 8 Hours
Preparing the Requirement Document | Detailed reuirement analysis and change management | 6 Hours
regular class meeting | Discuss the ongoing progress | 30 Min
| Total | 18 Hours 30 Min
Week-4
Start Date - 11/17/2016
End Date - 11/24/2016
Task | Description | Hours
Referring the documents and changing the | Reviewing the documents for improvements | 12
Week-5 | Total | 12
Start Date - 11/25/2016
End Date - 11/2/2016
Task | Description | Hours
Meeting with sponsor | Identification of some of the new requirement for the project | 1
Design Change | Changing the model according to the requirements | 12
Doumentation change | Inclusion if the new requirements in SRS | 3
Final Documention and submission | Preparing the video and log file | 3
| Total | 18